## Schedule
Activity ID | Activity Description | Start Date | End Date | Subcontractor | Foreman | Manpower | Equipment Loading | Critical Path | Completion
1 | Form Deck - Level 1 | 2023-10-25 | 2023-10-26 | SubA |  | 8
2 | Insert MEPs - Level 1 | 2023-10-26 | 2023-10-27 | SubB |  | 4
3 | Pull Rebar - Level 1 | 2023-10-27 | 2023-10-28 | SubC |  | 12
4 | Insert embeds and EOS itesm - level 1 | 2023-10-28 | 2023-10-29 | SubA |  | 3
5 | Quality control check and verify for concrete pour - Level 1 | 2023-10-29 | 2023-10-30 | SubA |  | 2
6 | Pour Concrete - Level 1 | 2023-10-30 | 2023-10-31 | SubD |  | 15
7 | Finish and Cure - Level 1 | 2023-10-31 | 2023-11-01 | SubD |  | 5
8 | Strip Formwork and recycle - Level 1 | 2023-11-01 | 2023-11-02 | SubA |  | 8
9 | Form Deck - Level 2 | 2023-11-02 | 2023-11-03 | SubA |  | 8
10 | Insert MEPs - Level 2 | 2023-11-03 | 2023-11-04 | SubB |  | 4
11 | Pull Rebar - Level 2 | 2023-11-04 | 2023-11-05 | SubC |  | 12
12 | Insert embeds and EOS itesm - level 2 | 2023-11-05 | 2023-11-06 | SubA |  | 3
13 | Quality control check and verify for concrete pour - Level 2 | 2023-11-06 | 2023-11-07 | SubA |  | 2
14 | Pour Concrete - Level 2 | 2023-11-07 | 2023-11-08 | SubD |  | 15
15 | Finish and Cure - Level 2 | 2023-11-08 | 2023-11-09 | SubD |  | 5
16 | Strip Formwork and recycle - Level 2 | 2023-11-09 | 2023-11-10 | SubA |  | 8
17 | Form Deck - Level 3 | 2023-11-10 | 2023-11-11 | SubA |  | 8
18 | Insert MEPs - Level 3 | 2023-11-11 | 2023-11-12 | SubB |  | 4
19 | Pull Rebar - Level 3 | 2023-11-12 | 2023-11-13 | SubC |  | 12
20 | Insert embeds and EOS itesm - level 3 | 2023-11-13 | 2023-11-14 | SubA |  | 3
21 | Quality control check and verify for concrete pour - Level 3 | 2023-11-14 | 2023-11-15 | SubA |  | 2
22 | Pour Concrete - Level 3 | 2023-11-15 | 2023-11-16 | SubD |  | 15
23 | Finish and Cure - Level 3 | 2023-11-16 | 2023-11-17 | SubD |  | 5
24 | Strip Formwork and recycle - Level 3 | 2023-11-17 | 2023-11-18 | SubA |  | 8
`
Formulas:
End Date = [Start Date]+1

## BOM
Material BOM
Formwork | Posts | 500
| LVL 5' | 200
| LVL 6' | 300
| ProDeck 5' | 300
| ProDeck 6' | 300
| Misc Material (clips, braces, etc.) | 220
MEP | MEP inserts/hangers | 1000
Rebar | Post tension cables (20') | 100
| Dowels | 300
| Formsavers | 300
Embeds | Edge of Slab embeds | 1000
| Anchor bolts | 200